## 32RA
Car Maker | Model | Product | Event | Items | Requestor | Requested Date | Department | PIC | Duedate | Status | Action Date
Honda | 32RA | 32200 | EV-MS | Request to delete rcot 5 L-85 on sub5 & reflect on Sub drawing and TCL-BR on sub 7, Delete pants/ Edit data | S.Silva | 2023-06-29 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32200 | EV-MS | Request to delete rcot5 L-320 on sub 6 & reflect on sub drawing/Delete/edit Data | S.Silva | 2023-06-29 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32200 | EV-MS | Request to change color of veq of shiase Left & right/ Color of seqvence | M.Roman | 2023-07-13 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32200 | EV-MS | Post all OI on form sub to all inspection process/ Posting OI | M.P Madona | 2023-06-10 | MPPD2 | M. Frane | 2023-06-24 | Closed | 2023-07-20
Honda | 32RA | 32200 | EV-MS | Revision of oi markings on band tie for fuse box, Add markings on other side of fuse of band tie/Revision of oi cyki-140-E | Pau | 2023-06-10 | MPPD2 | M. Frane | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32200 | EV-MS | Revision of oi for combine branch sect 22 due to not same picture of falp condition/Revision of oi cyki-133 | Pau | 2023-06-10 | MPPD2 | M. Frane | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32200 | EV-MS | Revision of oi for combine branch sect ajaj due to not same picture of falp condition/Revision of oi cyki-103-3 | Pau | 2023-06-10 | MPPD2 | M. Frane | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32200 | EV-MS | Revision of oi for combine lor. sect EE due to not same picture of falp condition/Revision of oi cyki-123 | Pau | 2023-06-23 | MPPD2 | M. Frane | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32200 | EV-MS | Request to change clamp jig on shiage to pokayoke/Pokayoke |  | 2023-07-23 | MPPD1 | I. Bocateja |  | Open
Honda | 32RA | 32200 | EV-MS | Request to adjust jig A58, Using actual harness which is jig #58 in applicable on EG inpection Board/Adjust jig #58 |  |  | MPPD1 | I. Bocateja |  | Open
Honda | 32RA | 32200 | EV-MS | Request to provide jig on clamp for dimension same as nbox (TTA) seq.101, 103 & 104 | Pau | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-16 | Cancelled | 2023-06-16
Honda | 32RA | 32200 | EV-MS | Request to provide or hole for conn. 134 w/ um.jig same as TTA nbox seq.68 | Pau | 2023-03-03 | MPPD1 | I. Bocateja | 2023-06-16 | Cancelled | 2023-06-16
Honda | 32RA | 32200 | EV-MS | Request to buff improvise jig for combine sect Ajaj Board 13/¦Buff | Kath Agonos | 2023-06-28 | MPPD1 | I. Bocateja |  | Open
Honda | 32RA | 32200 | EV-MS | Request to provide improvise jig for Band kme (BND kme) in ECT process/Improvise jig of Band Kme on ECT | M.Roman | 2023-06-03 | AME | Ame | 2023-06-21 | Open
Honda | 32RA | 32200 | EV | Request to change improvise jig the clamp jig an band tie detection jig on App and ECT inspection/Detection jig | Kath Agonos | 2023-06-24 | AME | L. Mercado | 2023-08-09 | Closed | 2023-08-09
Honda | 32RA | 32200 | EV | Request to separate the data of conn. Hus-Sb-12f & D5H- BA- 3E on Product F,G,I.C,D,E to Product A, B, H/Cheker jig | J.Bagui | 2023-06-26 | AME | L. Mercado | 2023-08-10 | Closed | 2023-08-10
Honda | 32RA | 32200 | EV-MS | Request to provide separate bando gun holder for NB 233-B on shicage due to different calibration (180 N 200 N) w/proper label of newton/Bando gun holder on shicage with proper label of calibration | Pau | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Labeling | 2023-06-16 | Open
Honda | 32RA | 32200 | EV-MS | Request to provide picture of all parts attached on ect on tupper box provided. Fuse c.clamp, lever,conn.corer , jetc./Picture of all parts on tupper box (ECT) | Pau | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | PE PREP | 2023-06-22 | Closed | 2023-06-22
Honda | 32RA | 32200 | EV-MS | Request to provide Foam on shicage board on portion of conn 113 FLB-32F/Foam for shicage Board | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | PE PREP | 2023-07-20 | Cancelled | 2023-07-20
Honda | 32RA | 32200 | EV-MS | Request to provide foam for tight Detector jig on Torque process/Foam for tight Detective jig | M. Roman | 2023-06-04 | PE-Prep, FAB (LFab, HFab & MFab) | FAB |  | Open
Honda | 32RA | 32117 | EV-MS | Request to provide shikakari holder on sub 14 and sub 17 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | A. De Torres |  | Open | 2023-06-16
Honda | 32RA | 32117 | EV | Request to provide vinyl cover on all sub pc board cover | Mosh | 2023-06-01 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andew | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV | Request to provide vinyl cover on downspout at the back of downspout | Mosh | 2023-06-01 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV | Request to resequence parts label on parts rack | Rosh | 2023-06-02 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling Tweety | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV | Request to provide shikakari label holder on sub 04,14,16,17 | Rosh | 2023-06-05 | PE-Prep, FAB (LFab, HFab & MFab) | A. De Torres | 2023-06-29 | Open
Honda | 32RA | 32117 | EV | Request to provide connection pic and label on beam plate | Rosh | 2023-06-05 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling | 2023-06-29 | Open
Honda | 32RA | 32117 | EV-MS | Request to provide Danpla for connection reference on assy board |  | 2023-06-15 | PE-Prep, FAB (LFab, HFab & MFab) | Glenn/Tweety | 2023-08-03 | Closed | 2023-08-03
Honda | 32RA | 32117 | EV-MS | Request to provide picture on tupper box for TCL-101-W on sub 14 | Rosh | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to provide component parts name and picture HSE 4m on ECT | Pau | 2023-06-27 | PE-Prep, FAB (LFab, HFab & MFab) | Labeling | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to provide component parts name and picture TCL203-b on shiage | Pau | 2023-06-27 | PE-Prep, FAB (LFab, HFab & MFab) | Labeling | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to provide component parts name picture TCL-115-DGR on ECT | Pau | 2023-06-27 | PE-Prep, FAB (LFab, HFab & MFab) | Labeling | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to remove baseplate of checker jig for connection 116 JSN-12F-GR then add cover same as checker jig for conn. 4 HSE-5PA | Pau | 2023-06-08 | AME | L. Mercado | 2023-06-30 | Open | 2023-08-03
Honda | 32RA | 32117 | EV-MS | Provide temporary tag fr NG checker jig for RYB conn. (2 portion) | Pau | 2023-06-08 | AME | L. Mercado | 2023-06-21 | Open
Honda | 32RA | 32117 | EV-MS | Offline Board |  | 2023-06-15 | AME | L. Mercado |  | Open
Honda | 32RA | 32117 | EV-MS | Request to provide indication of facing of conn. jig on assy board Conn 7 - must be facing/align to clamp jig Conn 176 - must be facing/align to SPJ Conn 141 - must be facing/align to U-jig | Pau | 2023-06-06 | MPPD2 | M. De Guzman | 2023-06-16 | Cancelled | 2023-06-16
Honda | 32RA | 32117 | EV-MS | Request to change junction jig on near portion 113-B Assy board |  | 2023-06-27 | MPPD1 | Ivan | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to provide option tape box on Dim 2 | Pau | 2023-06-27 | PE-Prep, FAB (LFab, HFab & MFab) | A. De Torres | 2023-07-06 | Closed | 2023-07-06
Honda | 32RA | 32117 | EV-MS | Request to provide label for max. set on inspection hanger | Pau | 2023-06-27 | PE-Prep, FAB (LFab, HFab & MFab) | M. Briones | 2023-07-06 | Closed | 2023-07-06
Honda | 32RA | 32117 | EV-MS | Request to fix seq. 38 and 39 due to double seq. on Dim 2 ( need re-sequence) | Pau | 2023-06-27 | MPPD1 | I. Bocateja | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32117 | EV-MS | Remove seq. 70 and 25 on Dim 2. Note: seq 70 is for 30-A+- 10 on acrylic option tape | Pau | 2023-06-27 | MPPD1 | I. Bocateja | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32117 | EV-MS | Request to change arrow direction of seq. 55 on Dim. 1 | Pau | 2023-06-27 | MPPD1 | I. Bocateja | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32117 | EV-MS | Request to buff 3d on LA seq. 81 Dim 1 | Pau | 2023-06-27 | MPPD1 | I. Bocateja | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32117 | EV-MS | Request to provide 3D on set. 70 on Dim 1 | Pau | 2023-06-27 | MPPD1 | I. Bocateja | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32117 | EV-MS | Request to buff conn. 153 on assy board 5 | Rosh | 2023-06-01 | MPPD1 | Ivan | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to provide sample clamp on Assy board 1 and shiage | Rosh | 2023-06-15 | MPPD1 | Ivan | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32117 | EV-MS | Request to change junction jig size |  | 2023-06-15 | MPPD1 | Ame | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to change location of SRT on option seq. 6 |  | 2023-06-15 | MPPD1 | Ame | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to remove seq. 25 and 24,26 on dim 2. |  | 2023-06-15 | MPPD1 | Ame | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32117 | EV-MS | Request to change conn. jig on shiage from SU to SR 102 | Pau | 2023-06-06 | MPPD1 | Ivan | 2023-06-24 | Closed | 2023-06-24
Honda | 32RA | 32117 | EV-MS | Request to provide seperate tanmatsu for conn 135 | Angel |  | MPPD1 | I. Bocateja | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32200 | EV-MS | Request to provide component #3 on branch 134/Component #3 | A.Zara | 2023-06-10 | MPPD2 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | EV-MS | Request to provide tape for all Board ft 191 & vt0.7 & 17 B/ Indication tape holder | M.Kamab | 2023-06-24 | MPPD2 | M. Mean | 2023-06-27 | Cancelled | 2023-06-27
Honda | 32RA | 32200 | EV-MS | Transfer location of 3D on Dimension process seq. 70 | M. Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | EV-MS | Request to improve stand of bukumi stand (Stant position)/Stand of Bukumi Brand | M.Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-08 | Closed | 2023-06-08
Honda | 32RA | 32200 | EV-MS | Request to change temporary jig to u jig on all board in branch w/ component #22 | M.Roman | 2023-06-06 | MPPD1 | I. Bocateja | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | EV-MS | Request to adjust jig for Pr-LL40/Adjust of jig of Pr LL40 | J.Bagui | 2023-06-06 | MPPD1 | I. Bocateja | 2023-06-08 | Closed | 2023-06-08
Honda | 32RA | 32200 | EV-MS | Request to change position of junction jig to left side near branch 113/Change position of junction jig | M.Roman | 2023-06-10 | MPPD1 | I. Bocateja | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32200 | EV-MS | Tape indication on all board FT 19 vto.7x 17 (B)/Tape holder | M.Roman | 2023-06-13 | MPPD1 | Sir ivan | 2023-06-27 | Cancelled | 2023-06-27
Honda | 32RA | 32200 | EV-MS | Request to change straight jig to bendable jig clamp nb.233.B near conn. 188 on shicage board/Bendable jig | k.Agonos | 2023-06-24 | MPPD1 | I. Bocateja | 2023-06-27 | Closed | 2023-06-27
Honda | 32RA | 32200 | EV-MS | Request to change improvise jig near branch clamp #41/improvise jig | A.Zara |  | MPPD1 | I. Bocateja | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV-MS | request to removed clamp jig mb-16 near Branch #13/Clamp jig | M. Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-03 | Closed | 2023-06-03
Honda | 32RA | 32109 | RC-EV | Request to rotate conn. Hyy-Sb-6F-1-B on sub drawing/Rotate conn pic | C.Malalvan | 2023-06-14 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to transfer taping of grommet from assy to bukumi/Additional bukumi board | J.Silva | 2023-06-16 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to provide nameplate holder (Airbag)on all boards/name plate holder for airbag | J.Silva | 2023-06-14 | MPPD1 | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to improve clamp jig #18 14A.185.OGR/Improve clamp jig NA-185-OGR | J.Silva | 2023-06-03 | MPPD1 | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to change the label of one set supply parts box |  | 2023-06-24 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to modify ins-hanger/Modify inspection hanger |  | 2023-06-29 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to provide beam for joint on sub3 5pcs/provide beam for joint | L.Cabungap | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman |  | Open
Honda | 32RA | 32751 | RC-EV | Request to provide beam for joint on sub3/Provide beam | L.Cabungap | 2023-06-10 | EM-Final/Initial | M. De Guzman | 2023-06-29 | Open
Honda | 32RA | 32751 | RC-EV | Request to change view of connector jig for combine of conn. and cord/connector checker jig | J.Silva | 2023-06-26 | MPPD1 | M. De Guzman | 2023-06-29 | Open
Honda | 32RA | 32752 | RC-EV | Request to provide sample clamp all boards/Provide sample clamp |  | 2023-06-16 | MPPD1 | M. De Guzman |  | Open
Honda | 32RA | 32752 | RC-EV | Request to buff conn. jig hse/ysna-25f/buff conn.jig hse/ysna-25f |  | 2023-06-23 | MPPD1 | M. De Guzman |  | Open
Honda | 32RA | 32752 | EV | Request to change the label of one part set supply/Change label seq of one part set supply |  | 2023-06-24 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman |  | Open
Honda | 32RA | 32117 | EV-MS | Request to provide subdrawing holder for sub 12,7,2,14 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Andrew | 2023-06-10 | Closed | 2023-06-10
Honda | 32RA | 32117 | EV-MS | Request to provide vinyl cathcer for tupperbox of sub 11, 17 on sub hanger | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Andrew | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to provide shikakari label on sub 14 220 R/, 533 G/, 248 BR/, 588BE/, 315 W/, 238 W/, 316 L/, 222 W/ ,446 GR/, 519 BR/ | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Andrew | 2023-06-10 | Closed | 2023-06-10
Honda | 32RA | 32117 | EV-MS | Request to provide shikakari label on sub 17 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep Glenn | 2023-06-10 | Closed | 2023-06-10
Honda | 32RA | 32117 | EV-MS | Request to provide tupperbox of TCL-115-DGK w/ picture on ECT process | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep Glenn | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32117 | EV-MS | Request to provide tupperbox w/ label or picture of clamp 2,3 and component 11 on bukumi A/B | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep Glenn | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to provide sample picture of conn. AFU-BTGA9010 on sub 14 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep Glenn | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32117 | EV-MS | Request to fix the tupperbox of locked of NG connector on sub 14 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Andrew | 2023-06-10 | Closed | 2023-06-10
Honda | 32RA | 32117 | EV-MS | Request to provide sample picture of the HSE-SFA on sub 12 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Maricon/Twedy | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV | Request to provide big tupper box for conn YSN-22M | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Glenn | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV | Request to change design of wire cathcer on sub from prt sub pc to combine one catcher per continous sub | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV | Request to provide vinyl cover on both ends of roller beam | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32117 | EV | Request to provide bando gun holder on bukumi | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV | Request to provide nameplate holder (roller) on bukumi | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV | Request to provide label on open downspout | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Tweety | 2023-06-26 | Cancelled | 2023-06-26
Honda | 32RA | 32117 | EV | Request to improve wire catcher on bukumi | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV | Request to transfer joint downspout from sub 7 to sub 8 and improve | Jane | 2023-06-02 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32117 | EV-MS | Request to provide joint hanger on sub 12 | Rosh | 2023-06-02 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Sir Andrew | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32117 | EV-MS | Request to fix nameplate holder on masterboard | Rosh | 2023-06-05 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Sir Andrew | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to interchange conn. pic and number of HSE-2F on sub 12 | Rosh | 2023-06-05 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling Tweety | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV | Request to resequence conn pic and label on sub assy based on sub pc jigs | Rosh | 2023-06-05 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV | Additional hanger and beam for sub 8 |  | 2023-06-15 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32117 | EV-MS | Request to provide parts holder for 1 set supply on assy board 4,2,1,17,16 | Rosh | 2023-06-09 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32117 | EV-MS | Request to fix tupperbox on shiage and ECT | Rosh | 2023-06-09 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Sir Andrew | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32117 | EV-MS | Request to provide shikakari label on sub 16 for joint 501,667,666, 668, 673, 669,670 | R. Acones | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32117 | EV-MS | Request to provide conn. pic and label on sub 14 on conn, HK-12M on tupper box | R. Acones | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-06-24 | Closed | 2023-06-24
Honda | 32RA | 32117 | EV-MS | Request to fix vinyl for RCOT 93 and 98 on parts | Rosh | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-06-24 | Closed | 2023-06-24
Honda | 32RA | 32117 | EV-MS | Request to provide conn. pic & label for RH-HGT2540F-DGR on sub 16 on tupperbox | Rosh | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-06-24 | Closed | 2023-06-24
Honda | 32RA | 32117 | EV-MS | Request to provide shikakari label on sub 2 at the back for shikakari 304, 211, 215,140,538,221, 282, 281, 417, 130, 104, 0128, 127, 119 | Rosh | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32117 | EV-MS | Request to provide connector pic. of 14K-L2M | M. Suasa | 2023-06-21 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Glenn | 2023-06-24 | Closed | 2023-06-24
Honda | 32RA | 32117 | EV-MS | Request to remove sub pc jig for OBDJ-16F on sub 02 | Rosh | 2023-05-30 | EM-Final/Initial | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to provide sample picture of conn. JSN-12F-GR & HSE/YSN9-28M on conn. tray of sub 3 | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep Glenn | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to provide kanban holder in all sub assy hanger | She C | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Sir Andrew | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to provide conn. sample picture on all sub PC | Jeza | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Glenn | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32117 | EV-MS | Request to change conn. sample picture from HSE-12F-1 to HSE-12F-1-L | Jeza | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Glenn | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to change shikakari label on shield wire from 684, 685, 686 to 676, 677, 678 on sub 17 | Jeza | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Glenn | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32117 | EV-MS | Request to provide conn. picture HSE/YSN9-2M on sub 6, 9 11 | Michelle | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Glenn | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Request to provide/install line no. | Rosh | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 6/31 | Closed | 2023-05-31
Honda | 32RA | 32117 | EV-MS | Request to improve roller beams | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-05-31 | Closed | 2023-05-31
Honda | 32RA | 32117 | EV-MS | Request to cut slider per continous sub | Angel | 2023-05-31 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to provide vinyl catcher for tupperbox on sub | Michelle | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-05-31 | Closed | 2023-05-31
Honda | 32RA | 32117 | EV-MS | Request to provide conn. tray for JSN-3F-GR 256 on sub 17 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Sir Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Request to provide tupper box for conn. 249 HGT-40F-B on sub 15 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Glenn | 2023-05-31 | Closed | 2023-05-31
Honda | 32RA | 32117 | EV-MS | Request to remove 1 conn. tray on sub 16 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32752 | EV | Request to modify ins.hanger/Modify inspection hanger. 5 hanger. |  | 2023-06-24 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman |  | Open
Honda | 32RA | 32752 | RC-EV | Request to provide beam for joint on sub/Provide beam for joint | L.Cabungap | 2023-07-20 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32752 | RC-EV | Request to provide beam for joint on sub/Provide beam for joint on sub | L.Cabungap | 2023-06-13 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32200 | RT | Request to delete RCOT 5 L-85 on sub 5 and reflect on sub drawing and TCL-BR on sub 7 | S. Silva | 2023-06-29 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32200 | RT | Request to delete RCOT5 L-320 on sub 6 and reflect on sub drawing | S. Silva | 2023-06-29 | MPPD2 | M. De Guzman | 2023-07-19 | Open
Honda | 32RA | 32200 | RT | Request to change color of seq of shiage left and right | S. Silva | 2023-07-03 | MPPD2 | M. De Guzman |  | Open
Honda | 32RA | 32200 | RT | Request to adjust the view of LA jig 151,167,166,27,105 on board 13,11 | J. Anglasan | 2023-06-29 | MPPD1 | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32200 | RT | Request to buff improvised jig on board 13 near branch 170 | J. Anglasan | 2023-06-29 | MPPD1 | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32200 | RT | Request to provide locket on clamp jig 19 on all board | R. Mendoza | 2023-06-10 | MPPD1 | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32200 | RT | Request to provide bend cover on all board | M. Roma | 2023-06-10 | MPPD1 | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32200 | RT | Request to change bending position of receiving jig clamp NB-162-W | Cherry | 2023-06-10 | MPPD1 | M. De Guzman | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32200 | RT | Request to change klipyoko jig on seq 3 and near ser. 23 on dimension inspection table |  | 2023-06-10 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32200 | RT | Request to change clamp jig on shiage to poka yoke |  | 2023-07-03 | MPPD1 | I. Bocateja |  | Open
Honda | 32RA | 32200 | RT | Request to provide tanmatsu for all board LA jig and conn 187 and near conn 190 |  | 2023-07-03 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32200 | RT | Request to adjust jig 58 using actual harness whic is jig 58 is applicabe on ECt inspection board |  | 2023-07-04 | MPPD1 | I. Bocateja |  | Open
Honda | 32RA | 32200 | EV | Request to change position of CL-connect for receiving jig of conn 54 | Jhona | 2023-06-10 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32200 | EV | Request to change bending position of junction jig | Cherry | 2023-06-10 | MPPD1 | I. Bocateja |  | Cancelled
Honda | 32RA | 32200 | EV | Request to change bending position of receiving jig clamp NB-162-W 29 all boad | Cherry | 2023-06-10 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32200 | EV | Request to extension of vinyl cover cover on front of sub assy machine of conn. jig | M. Roman | 2023-06-13 | PE-Prep, FAB (LFab, HFab & MFab) | Fab | 2023-07-03 | Closed | 2023-07-03
Honda | 32RA | 32200 | EV | Request to change con. pre (HK L2F-6 To HK L2F in sub 3 | M. Roman | 2023-06-13 | PE-Prep, FAB (LFab, HFab & MFab) | Labelling | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32200 | EV | Request to provide holder of Hang signage of parts rack | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | RT | Request to provide foam on shiage board in portion of conn. 13 FLB-32F | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep | 2023-07-20 | Cancelled | 2023-07-20
Honda | 32RA | 32200 | EV | Request to modify sub drawing holder | M. Zara | 2023-06-20 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32200 | EV | Insufficient vinyl cover on back of sub 8 | M. Roman | 2023-06-20 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-07-03 | Closed | 2023-07-03
Honda | 32RA | 32200 | EV | Request to put cable tie in harness of conn. jig. | M. Roman | 2023-06-23 | PE-Prep, FAB (LFab, HFab & MFab) | MD | 2023-07-03 | Closed | 2023-07-03
Honda | 32RA | 32200 | RT | Request to provide foam for tight detector jig on torque process. | M. Roman | 2023-06-24 | PE-Prep, FAB (LFab, HFab & MFab) | FAB |  | Open
Honda | 32RA | 32200 | EV | Request to provide tupperbox for NG and good sample in torque | J. Diylon | 2023-06-27 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32200 | EV | Request to provide tape indication on all board. FT19 VTO7X19(B) | M. Roman | 2023-06-13 | MPPD1 | I. Bocateja |  | Open
Honda | 32RA | 32200 | EV | Request to change straight jig to bendable jig clamp NB-233-B near conn. 188 on shiage board | K. Agonos | 2023-06-24 | MPPD1 | M. De Guzman | 2023-06-27 | Closed | 2023-06-27
Honda | 32RA | 32200 | EV | Request to change size improvise jig near branch clamp 41 | A. Zara |  | MPPD1 | I. Bocateja |  | Open | 2023-06-27
Honda | 32RA | 32200 | EV | Request to renew clamp jig WB-162-WWAR branch 113 | M. Roman | 2023-06-03 | MPPD1 | M. De Guzman | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV | Request to adjustable clamp jig 100 B. 5,10,1,4,7 | I. Castillo | 2023-06-24 | MPPD1 | M. De Guzman | 2023-06-03 | Closed | 2023-06-03
Honda | 32RA | 32200 | EV | Request to change bending position on clamp jig 116 board 9 | I. Castillo | 2023-06-24 | MPPD1 | Sir Ivan | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV | Request to buff improvise jig near clamp 71 board 11 | I. Castillo | 2023-06-24 | MPPD1 | M. De Guzman | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV | Request to change 3D jig to transparent on dimension seq 168 and 178 | M. Bagui | 2023-06-26 | MPPD1 | Sir Ivan | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV | Request to change bending position of improvise of combine taping section HH all board | K. Agonos | 2023-06-26 | MPPD1 | M. De Guzman | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV | Request to change bending position of junction jig near sect YY | Jhona | 2023-06-26 | MPPD1 | M. De Guzman | 2023-06-29 | Closed | 2023-06-29
Honda | 32RA | 32200 | QC SLOPE | Provide SPJ ( bendable L-jig) for yellow markings on washer hose position on clamp NB-760-W on shiage | Pau | 2023-06-10 | MPPD1 | M. De Guzman | 2023-06-13 | Closed | 2023-06-13
Honda | 32RA | 32200 | QC SLOPE | Request to change straight jig to bendable jig conn jig II 100 board 13 | K. Agonos | 2023-06-15 | MPPD1 | M. De Guzman | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32200 | QC SLOPE | Request to provide top limit and vjig for PCY-2FC-6 | M. Roman | 2023-06-08 | MPPD1 | M. De Guzman | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32200 | QC SLOPE | Request to buff conn. jig on MTX/RYB on sub assy | Cherry | 2023-06-26 | MPPD1 | M. De Guzman | 2023-06-27 | Closed | 2023-06-27
Honda | 32RA | 32200 | QC SLOPE | Request to adjust stubber of toridashi on dim board seq 129 | Jhona | 2023-06-27 | MPPD1 | M. De Guzman | 2023-06-29 | Closed | 2023-06-29
Honda | 32RA | 32200 | QC SLOPE | Request to change size of U-jig near component 70 | Jhona | 2023-06-27 | MPPD1 | M. De Guzman | 2023-06-29 | Closed | 2023-06-29
Honda | 32RA | 32200 | QC SLOPE | Request to change position improvise combine jig near component 44 all board | Jhona | 2023-06-27 | MPPD1 | M. De Guzman | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | QC SLOPE | Request to put pin on dimension inspection board junctiona rea near seq 66 |  | 2023-07-06 | MPPD1 | M. De Guzman | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32200 | QC SLOPE | Request to buff improvise jig for combine sect Ajaj Board 13/¦Buff | K. Agonos | 2023-07-08 | MPPD1 | I. Bocateja | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32200 | QC SLOPE | Request of extension of vinyl cover on front of sub assy machine of conn jig | M. Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-17 | Cancelled | 2023-06-22
Honda | 32RA | 32200 | QC SLOPE | Request to change conn pic of HKL2F-6 to HK-L2F on sub 3 | M. Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-22 | Cancelled | 2023-06-22
Honda | 32RA | 32200 | QC SLOPE | Request to transfer shikakari 376/298 G/ 375/297 Y from sub 4 to sub 3 and reflect on sub data | M. Zara | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-22 | Cancelled | 2023-06-22
Honda | 32RA | 32200 | QC SLOPE | Request to transfer 230,231 GR/ from sub 3 to sub 4 and reflect on intial/kanban | M. Zara | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-22 | Cancelled | 2023-06-22
Honda | 32RA | 32200 | QC SLOPE | Request to provide tupperbox for kanban holder of tubes and connector in parts rock | M. Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-22 | Cancelled | 2023-06-22
Honda | 32RA | 32200 | EV | Request to proivde holder of hand signage on parts rack | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | QC SLOPE | Request to add data on sub 7 shikakari 109,110 on conn RYB-TTAA000210 110 on AEE-BA-J07A-B | M. Roman | 2023-06-03 | MPPD1 | I. Bocateja | 2023-06-17 | Cancelled | 2023-06-17
Honda | 32RA | 32200 | QC SLOPE | Request to put point markings on 143,149 GR/, Both terminal due to same terminal insertion on layout and sub assy | M. Roman | 2023-06-03 | MPPD1 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | QC SLOPE | Request to add data on sub 8 280,299 per applicable on con YRH-SB-12F | M. Roman | 2023-06-03 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32200 | QC SLOPE | Request to provide foam on shiage board in portion of conn. 13 FLB-32F | M. Roman | 2023-06-03 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32200 | QC SLOPE | Request to provide improvise jig for Band kme (BND kme) in ECT process | M. Roman | 2023-06-21 | AME | M. De Guzman | 2023-08-01 | Closed | 2023-08-01
Honda | 32RA | 32200 | QC SLOPE | Request to adjust height of checker jig on ECT |  | 2023-06-15 | AME | M. De Guzman | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32200 | QC SLOPE | Request to improvise stand for shiage | M. Zara | 2023-06-15 | AME | AME Ivan | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32200 | QC SLOPE | REquest to change location CL-connect conn 54 | K. Agonos | 2023-06-17 | AME | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32200 | QC SLOPE | Request to change bending of clamp 41 | A. Zara | 2023-06-15 | AME | AME Ivan | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32200 | QC SLOPE | Request to provide tanmatsu rubber on assyboard, all boards for layout hang of wire | A. Zara | 2023-06-14 | AME | AME Ivan | 2023-07-03 | Closed | 2023-07-03
Honda | 32RA | 32200 | QC SLOPE | Request to provide hanging yanchi | Marvin | 2023-07-04 | AME | M. De Guzman | 2023-06-30 | Closed | 2023-06-30
Honda | 32RA | 32200 | QC SLOPE | Request to change bending jig 24-119 to straight jig | MPPD1 | 2023-06-23 | AME | M. De Guzman | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32200 | QC SLOPE | Request to change position of RBOX conn. 113 |  | 2023-06-23 | AME | M. De Guzman | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32200 | QC SLOPE | Request to change bending position of junction near conn 113 |  | 2023-06-18 | AME | M. De Guzman | 2023-06-18 | Closed | 2023-06-18
Honda | 32RA | 32200 | QC SLOPE | Request to provide/put sequence of conn on beam on sub roler | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | Labeling (Pe-Prep) | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32200 | QC SLOPE | Request to put vinyl cover on system unit | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | Fab MD | 2023-06-13 | Closed | 2023-06-13
Honda | 32RA | 32200 | QC SLOPE | Request to provide vinyl on every edge of roller on subassy after sub hanger | M. Roman | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) | Fab | 2023-06-13 | Closed | 2023-06-13
Honda | 32RA | 32200 | QC SLOPE | REquest to provide tupperbox on all retainer lock for sub pc and provide label | M. Roman | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) | Pe-Prep | 2023-06-14 | Closed | 2023-06-14
Honda | 32RA | 32200 | QC SLOPE | Request to provide tupperbox for connector picture on ECT | M. Roman | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | Pe-Prep | 2023-06-10 | Closed | 2023-06-10
Honda | 32RA | 32200 | QC SLOPE | Request to add component 18 NB-204-B parts box and shelves | A.Zara | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | PE-FAB | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32200 | QC SLOPE | Request to provide RCOT holder 112,40,131,12,14,142 all boards | A.Zara | 2023-06-09 | PE-Prep, FAB (LFab, HFab & MFab) | Pe-Prep | 2023-06-22 | Closed | 2023-06-22
Honda | 32RA | 32200 | QC SLOPE | Request to change foam on conveyor | Jhona | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | EQ | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32200 | QC SLOPE | Request to provide separate bando gun holder for NB 233-B on shicage due to different calibration (180 N 200 N) w/proper label of newton/Bando gun holder on shicage with proper label of calibration | Pau | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Labelling | 2023-06-22 | Closed | 2023-06-22
Honda | 32RA | 32117 | EV-MS | Request to remove 4 conn tray on sub 15 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Request to remove 1 conn tray on sub 16 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Provide 2 conn. Tray on sub 2 for conn 141 HSE/YENA-25M and 223 JCO-12F-GR | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Remove 2 conn tray on sub 6 and 7 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Provide big tupperbox on sub 8 for conn. RYB-BTSA9010 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Glenn | 2023-05-31 | Closed | 2023-05-31
Honda | 32RA | 32117 | EV-MS | Provide 1 conn tray on sub 3 HSE/YSN9-25M | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Remove 3conn tray on sub 9 | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Andrew | 2023-05-30 | Closed | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Request to fix clamp checker jigs on dim 2 |  | 2023-06-15 | AME |  | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32117 | EV-MS | Request to resequence sub pc jig on sub pc 13,14,10,11,06,08 and 16 | Rosh | 2023-06-05 | EM-Final/Initial | Lomi | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32117 | EV-MS | Request to remove sub pc jig of HSE-4F conn. 10 on sub 02 | Rosh | 2023-06-05 | EM-Final/Initial | Lomi | 2023-07-07 | Cancelled | 2023-07-07
Honda | 32RA | 32117 | EV-MS | Request to provide sub pc jig for HSE-12F-1-L conn 218 on sub 5 from sub 16 | Rosh | 2023-06-05 | EM-Final/Initial | Lomi | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32117 | EV-MS | Request to provide barcode holder in all inspection and mousepad | She C | 2023-06-13 | EM-Final/Initial | Kenneth | 2023-07-20 | Closed | 2023-07-20
Honda | 32RA | 32117 | EV-MS | Request to provide parts holder for 1 set supply on assy board 4,2,1,17,16,7 | Rica | 2023-06-15 | EM-Final/Initial | Sir Lalap | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32117 | EV-MS | Request to provide separate tupperbox for each alignment on HSE-JC-12MT | Angel | 2023-06-17 | EM-Final/Initial | Ken | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32117 | EV-MS | Request to provide rotary lock on board 18 | Rosh | 2023-06-22 | EM-Final/Initial | Ken | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32117 | EV-MS | Request to repair NG; rotary lock on board 20 | Rosh | 2023-06-22 | EM-Final/Initial | Ken | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32117 | EV-MS | Request to provide color sensor (ITDD) on dim2 |  | 2023-06-15 | EM-Final/Initial | C. Lalap | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32117 | EV-MS | Request to delete TCL-115-DGR on conn 1 on subdrawing 3 | She C | 2023-05-30 | MPPD2 | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to delete on conn. 131 TCL-101W on sub drawing 4 | M. Pesimo | 2023-05-30 | MPPD2 | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to delete shikakari 964 Y/ joint 9 on sub 13 | C. Malaluan | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Reques to transfer shikakari 964 Y/ on layout | C. Malaluan | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to delete shikakari 294 VI/ on sub 7 conn. JSN-32F-GR transfer to layout | Michelle | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to transfer shikakaris 231 on sub 7 and kanban sub no from sub 2 | Rosh | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-02 | Cancelled | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to drop shikakari 102 on conn 10 on sub 2 | Rosh | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-02 | Closed | 2023-06-02
Honda | 32RA | 32117 | EV-MS | Request to change sub # of shikakari 504 Y/,133 W, 131LG from sub 5 to sub 13 | Mhara | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32117 | EV-MS | Request to change sub number of shikakari 414 and 413 R/ from sub 16 to sub 8 | Mhara | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32117 | EV-MS | Request to separate sub no. of similar conn HSE-12F-1 and HSE-12F-1-L affected sub = 16 | Pau | 2023-05-31 | MPPD2 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32117 | EV-MS | Request to delete TCL-101W on sub 4 | M. Pesimo | 2023-05-30 | MPPD1 | M. Frane | 2023-05-30 | Cancelled | 2023-05-30
Honda | 32RA | 32117 | EV-MS | Request to change arrow direction on seq 55 on Dim1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32117 | EV-MS | Change 3d of seq 36 to 43 on dim 1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32117 | EV-MS | Provide 3D for seq 82 LA 30 on dim board 1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32117 | EV-MS | Change seq. 32 max 55 to seq 34 on dim 1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32117 | EV-MS | Provide seq 39 must be max 45 near seq 38 on dim1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32117 | EV-MS | Request to extend 3d on seq 73 for max 38 on dim1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to resequence 77 to 83 on dim 1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to provide seq 85 near seq 87 on dim1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-21 | Closed | 2023-06-21
Honda | 32RA | 32117 | EV-MS | Request to change 3D mar seq 147 on dim 1 | Rosh/Paula | 2023-05-31 | MPPD1 | Ivan | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32117 | EV-MS | Request to change size of improvised jig near clamp 79 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to provide lockset for conn 222 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to reduce height conn 222 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to reduce height on conn 186 and 162 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to adjust 3d board to straight position near clamp 33 on shiage | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to reduce height clamp c19154 near conn 34 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to add height and buff clamp jig 63 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Adjust clamp jig 79 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to buff clamp jig 29 on shiage | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32117 | EV-MS | Request to add height and buff conn. YSN/HK2-10 on shiage board | Rosh/Paula | 2023-05-30 | MPPD1 | Ivan | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32752 | RC-EV | Request to improve clamp jig 18,39,42 NA 185-DGR | L. Cabungcal | 2023-06-03 | MPPD2 | M. De Guzman | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32752 | RC-EV | Request to adjust receiving jig of clamp 4 | L. Cabungcal | 2023-06-03 | MPPD2 | M. De Guzman | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32752 | RC-EV | Request to adjust reference jig on VTO 13X19(TR) | L. Cabungcal | 2023-06-03 | MPPD2 | M. De Guzman | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32752 | RC-EV | Request to provide connector tray on sub-assy on conn HSE-YSN9-25F | L. Cabungcal | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32752 | RC-EV | Request to provide nameplate holder on all boards @ airbag | L. Cabungcal | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32752 | RC-EV | Request to provide tupperbox for fallen parts damaged conn @ locked connector | L. Cabungcal | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32752 | RC-EV | Request to change wire catcher of auto grommet machine | L. Cabungcal | 2023-06-15 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32752 | RC-EV | Request to provide checksheet holder | L. Cabungcal | 2023-06-15 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32752 | RC-EV | Request to transfer location of component 41,25,39,42,53 @ 13 | L. Cabungcal | 2023-06-17 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32752 | RC-EV | Request to provide RCOT holder on board RCOT 5 L-480 | L. Cabungcal | 2023-06-17 | PE-Prep, FAB (LFab, HFab & MFab) | M. De Guzman | 2023-06-25 | Closed | 2023-06-25
Honda | 32RA | 32752 | RC-EV | Request to provide tape holder FT19(B) | L. Cabungcal | 2023-06-06 | MPPD1 | M. De Guzman | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32752 | RC-EV | Request to change the measurement on seq 31 @ seq 24 to optional | L. Cabungcal | 2023-06-06 | MPPD1 | M. De Guzman |  | Cancelled
Honda | 32RA | 32752 | RC-EV | Request to provide tape holder vto 07x19(B) all boards/provide tape holder | L. Cabungcal | 2023-06-16 | MPPD1 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32109 | RC-EV | Request to change seq 24 to optional on dimension board | J. Palmingco | 2023-06-06 | MPPD2 | M. De Guzman | 2023-06-17 | Closed | 2023-06-17
Honda | 32RA | 32109 | RC-EV | Request to optional seq 22 and seq 27 | C. Malaluan | 2023-06-22 | MPPD2 | M. De Guzman |  | Cancelled
Honda | 32RA | 32109 | RC-EV | Request to change seq 27 to optional on dimension board | J. Palmingco | 2023-06-06 | MPPD2 | M. De Guzman |  | Cancelled
Honda | 32RA | 32109 | RC-EV | Request to provide tape holder VTO7X19(B) | J. Palmingco | 2023-06-06 | MPPD1 | I. Bocateja | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32109 | RC-EV | Request to change seq 27 to optional on dim board | J. Palmingco | 2023-06-06 | MPPD1 | I. Bocateja |  | Cancelled
Honda | 32RA | 32109 | RC-EV | Request to change seq 24 to optional on dim board | J. Palmingco | 2023-06-06 | MPPD1 | I. Bocateja |  | Cancelled
Honda | 32RA | 32109 | RC-EV | Request to rotate conn. Hyy-Sb-6F-1-B on sub drawing/Rotate conn pic | C.Malaluan | 2023-06-14 | MPPD1 | I. Bocateja |  | Cancelled
Honda | 32RA | 32109 | RC-EV | Request to change conn. YSN-14F to YSN-22F on assy board 12 | J. Palmingco | 2023-06-22 | MPPD1 | I. Bocateja | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32109 | RC-EV | Request to buff clamp jig 23 in all board | J. Palmingco | 2023-06-22 | MPPD1 | I. Bocateja | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32109 | RC-EV | Request to provide nameplate holder,bando gun holder board 12 | J. Palmingco | 2023-06-22 | PE-Prep, FAB (LFab, HFab & MFab) | M.Briones | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32109 | RC-EV | Request to modify sub assy hanger | J. Palmingco | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | M.Briones | 2023-06-06 | Closed | 2023-07-06
Honda | 32RA | 32109 | RC-EV | Request to provide connector YSN-2F,PBSLEEVE, YSN-14F | J. Palmingco | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) |  |  | Open
Honda | 32RA | 32109 | RC-EV | Request to provide tupperbox for fallenparts,damage conn, lock conn | J. Palmingco | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) | M.Briones | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32109 | RC-EV | Request to provide conector tray on conn. YRHL-SB-2F-2DGR | L. Cabungcal | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-05 | Closed | 2023-06-05
Honda | 32RA | 32109 | RC-EV | Request to provide beam for join on sub | L. Cabungcal | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32109 | RC-EV | Request to provide tanmatsu onsub assy | C.Malaluan | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32109 | RC-EV | Request to provide tupper box and label HSE/YSN-4-28F YSN-3FA YSN-2F YSN-4M YSN-14F DHE-2F | C.Malaluan | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32109 | RC-EV | Request to provide conn pic and label | C.Malaluan | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32109 | RC-EV | Request to provide cathcer on sub assy | C.Malaluan | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32109 | RC-EV | Request to provide conn tray conn YRHL-SB-2F-1-GR HSE/YSN44-28F | C.Malaluan | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32109 | RC-EV | Request to provide sub drawing holder on sub assy | C.Malaluan | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) | Andrew | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32109 | RC-EV | Request to improve HYY-SB-6F on ECT board | J. Palmingco | 2023-06-06 | AME | L. Mercado | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32109 | RC-EV | Request to align the jig near on component 1 (all board) | C.Malaluan | 2023-06-22 | MPPD1 | I. Bocateja | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32109 | RC-EV | Request to additional height conn 35 for combine (all board) | C.Malaluan | 2023-06-22 | MPPD1 | I. Bocateja | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32109 | RC-EV | Request to lockset conn. 35 (all board) | C.Malaluan | 2023-06-22 | MPPD1 | I. Bocateja | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32129 | RC | Request to provide tape holder on assy | M. Pesimo | 2023-06-26 | MPPD1 | I. Bocateja | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32129 | RC | Request to provide parts overhead on assy board | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32129 | RC | Request to combine process label of ECT and dimension | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32129 | RC | Request to adjust height of inspection hanger from 800mm to 900mm | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Donna |  | Open
Honda | 32RA | 32129 | RC | Request to provide sub drawing holder on sub assy | M. Pesimo |  | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32129 | RC | Request to provide vinyl holder for groomet (GB0743) on Subassy | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew |  | Open
Honda | 32RA | 32129 | RC | Request to provide groomet opener on Sub assy | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew |  | Open
Honda | 32RA | 32129 | RC | Request to provide connector picture/holder/label on Sub PC | M. Noman | 2023-07-10 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Labeling | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 32129 | RC | Request to provide product number reference on assy board | M. Noman | 2023-07-10 | PE-Prep, FAB (LFab, HFab & MFab) | Labeling |  | Open
Honda | 32RA | 77901 | EV | Request to provide kanban holder on sub assy | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 77901 | EV | Request to provide Sub hanger on Sub assy | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew | 2023-07-10 | Closed | 2023-07-10
Honda | 32RA | 77901 | EV | Request to provide box on all inspection after inspect | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew |  | Open
Honda | 32RA | 77901 | EV | Request to provide process name on inspection | M. Pesimo | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | Tweety | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 77901 | EV | Request to additional beam hanger on Sub assy | M. Pesimo |  | PE-Prep, FAB (LFab, HFab & MFab) |  |  | Open
Honda | 32RA | 77901 | EV | Request to provide preffer hanger on assy board | M. Noman | 2023-07-11 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 77901 | EV | Request to provide picture connector holder/label on Sub PC | M. Noman | 2023-07-11 | PE-Prep, FAB (LFab, HFab & MFab) | Fab/Labeling | 2023-07-11 | Closed | 2023-07-11
Honda | 32RA | 77901 | EV | Request to provide pipe holder for product label on assyboard | She C | 2023-07-11 | PE-Prep, FAB (LFab, HFab & MFab) | FAB | 2023-07-12 | Closed | 2023-07-12
Honda | 32RA | 77901 | EV | Request to change nameplate holder into roll like 3043-32139 | M. Noman | 2023-07-13 | PE-Prep, FAB (LFab, HFab & MFab) | FAB |  | Open
Honda | 32RA | 77901 | EV | Request to fix the barcode scanner on dim/ECT board | She C | 2023-07-06 | EM-Final/Initial | Kenneth | 2023-07-07 | Closed | 2023-07-07
Honda | 32RA | 32200 | EV | Request to provide tupperbox for kanban holder for tubes 8 conn. on parts rock | M. Roman | 2023-06-03 | PE-Prep, FAB (LFab, HFab & MFab) | PE-Prep | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32117 | EV | Provide tupperbox on sub 07 for OBDJ-16F | Rosh | 2023-05-30 | PE-Prep, FAB (LFab, HFab & MFab) | Fab Glenn | 2023-05-31 | Closed | 2023-05-31
Honda | 32RA | 32751 | EV | Request to change wire catcher on grommet machine | G. Castro | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32751 | EV | Request to provide conn. picture on (HSE/YSNA-14F) | G. Castro | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Glen | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32751 | EV | Request to change the label of one set supply parts box |  | 2023-06-24 | PE-Prep, FAB (LFab, HFab & MFab) | M. Briones | 2023-07-05 | Closed | 2023-07-05
Honda | 32RA | 32751 | EV | Request to modify ins. hanger |  | 2023-06-24 | PE-Prep, FAB (LFab, HFab & MFab) | A. De Torres | 2023-07-19 | Closed | 2023-07-19
Honda | 32RA | 32751 | EV | Request to modify wire catcher on sub-assy all PC |  | 2023-06-26 | PE-Prep, FAB (LFab, HFab & MFab) | A. De Torres | 2023-07-08 | Closed | 2023-07-08
Honda | 32RA | 32751 | EV | Request for nameplate holder for additional board | Lg. Agdan | 2023-08-13 | PE-Prep, FAB (LFab, HFab & MFab) | Maam Donna | 2023-08-16 | Closed | 2023-08-16
Honda | 32RA | 32751 | EV | Request for product label holder on additional assy board | Lg. Agdan | 2023-08-13 | PE-Prep, FAB (LFab, HFab & MFab) | Maam Donna | 2023-08-16 | Closed | 2023-08-16
Honda | 32RA | 32751 | RC-EV | Request to provide tupper box on ASE-2F-YLE/DS4-10F | J. Silva | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32751 | RC-EV | Request to provide nameplate holder on all board and airbag | J. Silva | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-06-07 | Closed | 2023-06-07
Honda | 32RA | 32751 | RC-EV | Request to provide cnnector tray on connector HSE/YSN4-28F HSE/YSN4-14F | J. Silva | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32751 | RC-EV | Request to provide part box (one set supply) | J. Silva | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32751 | RC-EV | Request to provide tupper box for fallen parts, damanges parts, locked connector. | J. Silva | 2023-06-06 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-06-06 | Closed | 2023-06-06
Honda | 32RA | 32751 | RC-EV | Requet to provide beam for joint on Sub #3 (5 pcs.) | L. Cabungcal | 2023-06-10 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Andrew | 2023-06-29 | Closed | 2023-06-29
Honda | 32RA | 32751 | RC-EV | Request to provide sub drawing hanger in all sub pc | J. Silva | 2023-06-14 | PE-Prep, FAB (LFab, HFab & MFab) |  | 2023-06-15 | Closed | 2023-06-15
Honda | 32RA | 32751 | RC-EV | Request to change grommet catcher | J. Silva | 2023-06-15 | PE-Prep, FAB (LFab, HFab & MFab) | A. Detorres | 2023-06-26 | Closed | 2023-06-26
Honda | 32RA | 32751 | RC-EV | Request to provide RCOT holder on all board for RCOT 5 L-480 | J. Silva | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | A. Detorres | 2023-06-23 | Closed | 2023-06-23
Honda | 32RA | 32751 | RC-EV | Request to change sub pc label Sub 2 only | G. Castro | 2023-06-16 | PE-Prep, FAB (LFab, HFab & MFab) | Sir Gleen | 2023-06-23 | Closed | 2023-06-23
Toyota | 920B | 32107-LHD | CERT Request | Request to provide reference jig of end of RCOT #293 on bukumi board | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Reduce height of clamp jig #307 on bukumi board | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to provide receiving jig for clamp NB-204-B on bukumi board for combining of two branches(BR.362) | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Reduce height of grommet jig #304 and 323 on bukumi board | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to provide connector receiving jig #84 YSP-SB-2F-1-B on assy board near branch | A. Giledo | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to provide connector jig #103 YSQ-AB-B2FR-8R on assy board 87 | A. Giledo | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to provide grommet jig GB5468 near branch 50 on assy board | A. Giledo | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to provide conn jig #42 JMX36-B0-4FA-2X on assy board | A. Giledo | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to buff clamp jig NB-204-B near component #107 | A. Giledo | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Reqiuest to provide receiving jig for component #93 JSN/YSN4 24F on assy board | A. Giledo | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-02 | Closed | 2023-08-02
Toyota | 920B | 32107-LHD | CERT Request | Request to adjust SPJ on component 206 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to change sample clamp from NB162 to NB 162PK | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide SPJ to component 125 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide reference jig on component 209 212 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide SPJ on component 123 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide sample clamp 3 103 70 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide tape holder VT0.7x30(B) VT0 .07x90(B) | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide reference jig for component no 253 300 49 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to change bendable clamp jig on component 146 | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to additional heightof clamp jig NA-185-QGR for combining of branch | J. Barberan | 2023-08-02 | MPPD1 | M. Cuevas | 2023-08-03 | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to remove SPJ component #3 on assy board and #135 | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to provide SPJ for component #254 on assy board and #145 | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to bend the jig from straight to bendable jig (RYB-BT5A9010) on assy board | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to provide U jig for branch #362 SSE-SB-8F-GR on assy board | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to change sample clamp component #162 from NA-157-B to NA-157-PK-B on assy board | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to bendable jig connector #87 on assy board | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Cancelled
Toyota | 920B | 32107-LHD | CERT Request | Request to provide SPJ to component 290 | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to reduce height of clamp jig component no 87 on assy board | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to provide top limit for combining branch #131 on assy board | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to buff the clamp jig component no. 03 | A. Giledo | 2023-08-04 | MPPD1 | M. Cuevas | 2023-08-05 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to provide sample name plate holder | R. Mazo | 2023-08-01 | PREP/FAB |  | 2023-08-07 | Closed | 2023-08-07
Toyota | 920B | 32107-LHD | CERT Request | Request to provide sample clamp 3 103 | R. Mazo | 2023-08-03 | PREP/FAB |  |  | Cancelled
Toyota | 920B | 32107-LHD | CERT Request | Request to provide catcher for bukumi 20, bukumi 23 | A. Giledo | 2024-01-11 | PREP/FAB |  |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide conn. Reference of conn. 367 & 364 HVSMK2-BA-5F,4.B on bukumi board | J. Barberan |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide connector reference for conn. 254 YSQ-AB-B2FY-1-B on bukumi board | J. Barberan |  | MPPD2 | Mhean |  | Closed | 2023-08-31
Toyota | 920B | 32107-LHD | CERT Request | Provide applicability of insertion on conn. 111 YSN-18FA-G shikakari #212 LA/P on conn. Reference on assy b oard | A. Giledo |  | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Transfer location of conn. Reference of conn. 75 HSE/YSN4-28F near conn. Jig | A. Giledo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Provide applicable product for conn.51 STW-SBU-4F-DGR on assy board | A. Giledo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide picture of tape VTO0.7X90 and VTO0.7X30(B) on assy board and bukumi 20, Bukumi 23 | A. Giledo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide dummy layout branch 103, 100 | R. Mazo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide dummy layout branch 42 | R. Mazo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide dummy layout of grommet | R. Mazo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to provide dummy layout of bukumi A/B br. 360, 84 | R. Mazo |  | MPPD2 | Mhean |  | Closed | 2023-08-04
Toyota | 920B | 32107-LHD | CERT Request | Request to improve conn. 2, 75, 1, 147, 58 | R. Mazo | 2023-08-01 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide conn. Reference 274 | R. Mazo | 2023-08-04 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide view ASAS combine of clamp TB-6-1-B component no. 238 | R. Mazo | 2023-08-04 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide component no. on clamp NB-109 PK | J. Barberan | 2023-08-04 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide view ANAN combine of clamp NB-109-PK-B component no. 246 | R. Mazo | 2023-08-05 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to change layout branch 1, 82, 380 | R. Mazo | 2023-08-05 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to change location of component no. tampered by jig near branch 62 on assy board | A. Giledo | 2023-08-05 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to clarify on bukumi drawing due to not taly on dim. Drawing | J. Barberan | 2023-08-11 | MPPD2 | Mhean |  | Open
Toyota | 920B | 32107-LHD | CERT Request | Request to provide connector reference on 274 assy board |  | 2023-08-30 | MPPD2 | Mhean |  | Open